## Tabelle1
Prototypen Phase RemoteWorkstation | [5 empty] | Begin of Project: | 2016-04-18
[6 empty] | Today | 2016-04-07
[6 empty] | End of Project | 2016-06-10
[6 empty] | Project status: | 0%
Offene Punkte | [8 empty] | KW 17 | [6 empty] | KW 18 | [6 empty] | KW 19 | [6 empty] | KW 20 | [6 empty] | KW 21 | [6 empty] | KW 22 | [6 empty] | KW 23 | [6 empty] | KW 24 | [6 empty] | KW 25 | [6 empty] | KW 26 | [6 empty] | KW 27 | [6 empty] | KW 28 | [6 empty] | KW 29 | [6 empty] | KW 30 | [6 empty] | KW 31 | [6 empty] | KW 32 | [6 empty] | KW 33 | [6 empty] | KW 34
[9 empty] | 2016-04-18 | [6 empty] | 2016-04-25 | [6 empty] | 2016-05-02 | [6 empty] | 2016-05-09 | [6 empty] | 2016-05-16 | [6 empty] | 2016-05-23 | [6 empty] | 2016-05-30 | [6 empty] | 2016-06-06 | [6 empty] | 2016-06-13 | [6 empty] | 2016-06-20 | [6 empty] | 2016-06-27 | [6 empty] | 2016-07-04 | [6 empty] | 2016-07-11 | [6 empty] | 2016-07-18 | [6 empty] | 2016-07-25 | [6 empty] | 2016-08-01 | [6 empty] | 2016-08-08 | [6 empty] | 2016-08-15
 | time axis 2016-04-18 to 2016-08-25
Task | Processor | Effort(h) | Start | Durration | End | Progress | Status | time axis 2016-04-18 to 2016-08-25
Einarbeitung/Einrichtung |  | 16 | 2016-04-18 | 2 | 2016-04-19 | 0% |  | 2016-04-15
OpenVX Wrapper |  | 40 | 2016-04-19 | 5 | 2016-04-25 | 0%
VideoGrabber_SIMU |  | 24 | 2016-04-25 | 3 | 2016-04-27 | 0% |  | 2016-04-22
Graphic_ColorConvert |  | 10 | 2016-04-28 | 2 | 2016-04-29 | 0% |  | 2016-04-27
Encoder_NVIDIA |  | 80 | 2016-04-25 | 10 | 2016-05-06 | 0% |  | 2016-04-22
Decoder_Intel |  | 80 | 2016-04-25 | 10 | 2016-05-06 | 0% |  | 2016-04-22
Player_Lite |  | 80 | 2016-04-25 | 10 | 2016-05-06 | 0% |  | 2016-04-22
Encoder Settings |  | 12 | 2016-05-09 | 2 | 2016-05-10 | 0% |  | 2016-05-06
Decoder_Settings |  | 12 | 2016-05-09 | 2 | 2016-05-10 | 0% |  | 2016-05-06
Multiple Encoder Sessions |  | 24 | 2016-05-11 | 3 | 2016-05-13 | 0% |  | 2016-05-10
Multiple Decoder Sessions |  | 24 | 2016-05-11 | 3 | 2016-05-13 | 0% |  | 2016-05-10
Create 4K Frame |  | 20 | 2016-05-16 | 3 | 2016-05-18 | 0% |  | 2016-05-13
Cut 4K Bild |  | 20 | 2016-05-16 | 3 | 2016-05-18 | 0% |  | 2016-05-13
4K Bild Encode |  | 16 | 2016-05-19 | 2 | 2016-05-20 | 0% |  | 2016-05-18
4K Bild Decode |  | 16 | 2016-05-19 | 2 | 2016-05-20 | 0% |  | 2016-05-18
MetaDaten |  | 40 | 2016-05-23 | 5 | 2016-05-27 | 0% |  | 2016-05-20
AudioGrabber |  | 40 | 2016-05-23 | 5 | 2016-05-27 | 0% |  | 2016-05-20
Playback of Audio and Video |  | 80 | 2016-05-09 | 10 | 2016-05-20 | 0% |  | 2016-05-06
Streaming |  | 160 | 2016-05-09 | 20 | 2016-06-03 | 0% |  | 2016-05-06
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
| Summe | 794 |  | 102
Formulas:
End = WORKDAY(IF(WEEKDAY([Start],1)=7,[Start]+2,IF(WEEKDAY([Start],1)=1,[Start]+1,[Start])),[Durration]-1,)
Note on B8: Master: Hat Marcus bereits ein OPENCV für GPU ?
Note on B12: Master: Installation of the Toolchain and briefing of the concept.
Note on B15: Master: Convert the grabbed picture to YUV420 or YUV444 … Compare the durration of both. The implementation should use the GPU version. If time, compare it with the CPU Version
Note on B18: kunadt: Small lite player implemtenation for the first test steps.
Note on B19: Master: play with the sesstings of the econder and compare it.
Note on B20: Master: play with the settings of the decoder and compare it.
Note on B21: Master: It should be possible to run 2 seperate encoder sessions. Take benchmarks to compare against a single session
Note on B22: Master: It should be possible to run 2 seperate decoder sessions. Take benchmarks to compare against a single session
Note on B26: Master: How does a 4k build avoid of the performance. How many FPS can we reach
Note on B27: Master: How the amount of meta data avoid the performance of the encoding.
Note on B29: Master: Pipline from audo and video grab to the display in the local player