## Tabelle1
Prototypen Phase RemoteWorkstation |  |  |  |  | Begin of Project: | 2016-03-07
[5 empty] | Today | 2016-02-25
[5 empty] | End of Project | 2016-05-06
[5 empty] | Project status: | 0%
Offene Punkte | [7 empty] | KW 11 | [6 empty] | KW 12 | [6 empty] | KW 13 | [6 empty] | KW 14 | [6 empty] | KW 15 | [6 empty] | KW 16 | [6 empty] | KW 17 | [6 empty] | KW 18 | [6 empty] | KW 19 | [6 empty] | KW 20 | [6 empty] | KW 21 | [6 empty] | KW 22 | [6 empty] | KW 23 | [6 empty] | KW 24 | [6 empty] | KW 25 | [6 empty] | KW 26 | [6 empty] | KW 27 | [6 empty] | KW 28
[8 empty] | 2016-03-07 | [6 empty] | 2016-03-14 | [6 empty] | 2016-03-21 | [6 empty] | 2016-03-28 | [6 empty] | 2016-04-04 | [6 empty] | 2016-04-11 | [6 empty] | 2016-04-18 | [6 empty] | 2016-04-25 | [6 empty] | 2016-05-02 | [6 empty] | 2016-05-09 | [6 empty] | 2016-05-16 | [6 empty] | 2016-05-23 | [6 empty] | 2016-05-30 | [6 empty] | 2016-06-06 | [6 empty] | 2016-06-13 | [6 empty] | 2016-06-20 | [6 empty] | 2016-06-27 | [6 empty] | 2016-07-04
 | time axis 2016-03-07 to 2016-07-14
Aufgabe | Bearbeiter | Start | Dauer | Ende | Fortschritt | Status | time axis 2016-03-07 to 2016-07-14
Einarbeitung/Einrichtung |  | 2016-03-07 | 2 | 2016-03-08 | 0% |  | 2016-03-04
VideoGrabber_SIMU |  | 2016-03-09 | 3 | 2016-03-11 | 0% |  | 2016-03-08
Graphic_ColorConvert |  | 2016-03-12 | 2 | 2016-03-15 | 0% |  | 2016-03-11
Encoder_NVIDIA |  | 2016-03-09 | 10 | 2016-03-22 | 0% |  | 2016-03-08
Decoder_Intel |  | 2016-03-09 | 10 | 2016-03-22 | 0% |  | 2016-03-08
Player_Lite |  | 2016-03-09 | 10 | 2016-03-22 | 0% |  | 2016-03-08
Encoder Settings |  | 2016-03-16 | 3 | 2016-03-18 | 0% |  | 2016-03-15
Decoder_Settings |  | 2016-03-16 | 3 | 2016-03-18 | 0% |  | 2016-03-15
Multiple Encoder Sessions |  | 2016-03-21 | 3 | 2016-03-23 | 0% |  | 2016-03-18
Multiple Decoder Sessions |  | 2016-03-21 | 3 | 2016-03-23 | 0% |  | 2016-03-18
Create 4K Frame |  | 2016-03-24 | 3 | 2016-03-28 | 0% |  | 2016-03-23
Cut 4K Bild |  | 2016-03-24 | 3 | 2016-03-28 | 0% |  | 2016-03-23
4K Bild Encode |  | 2016-03-29 | 1 | 2016-03-29 | 0% |  | 2016-03-28
4K Bild Decode |  | 2016-03-29 | 1 | 2016-03-29 |  |  | 2016-03-28
MetaDaten |  | 2016-03-30 | 2 | 2016-03-31 |  |  | 2016-03-29
AudioGrabber |  | 2016-03-30 | 5 | 2016-04-05 |  |  | 2016-03-29
Playback of Audio and Video |  | 2016-04-01 | 10 | 2016-04-14 |  |  | 2016-03-31
Streaming |  | 2016-04-06 | 18 | 2016-04-29 |  |  | 2016-04-05
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
#NUM!
Formulas:
Ende = WORKDAY(IF(WEEKDAY([Start],1)=7,[Start]+2,IF(WEEKDAY([Start],1)=1,[Start]+1,[Start])),[Dauer]-1,)
Note on B8: Master: Hat Marcus bereits ein OPENCV für GPU ?
Note on B12: Master: Installation of the Toolchain and briefing of the concept.
Note on B14: Master: Convert the grabbed picture to YUV420 or YUV444 … Compare the durration of both. The implementation should use the GPU version. If time, compare it with the CPU Version
Note on B18: Master: play with the sesstings of the econder and compare it.
Note on B19: Master: play with the settings of the decoder and compare it.
Note on B20: Master: It should be possible to run 2 seperate encoder sessions. Take benchmarks to compare against a single session
Note on B21: Master: It should be possible to run 2 seperate decoder sessions. Take benchmarks to compare against a single session
Note on B25: Master: How does a 4k build avoid of the performance. How many FPS can we reach
Note on B26: Master: How the amount of meta data avoid the performance of the encoding.
Note on B28: Master: Pipline from audo and video grab to the display in the local player